## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Backend | 46061 | Missing values and null entries found in Azure usage dataset causing pipeline failures during preprocessing | Sprint 1 | Backend | Logical | Applied imputation for numeric fields and dropped rows with >30% null values; standardized column formats | 46062 | Closed | Detected during initial data validation step
2 | Backend | 46064 | Inconsistent date formats across regional datasets causing merge errors in pandas | Sprint 1 | Backend | Logical | Unified all date columns to ISO 8601 format (YYYY-MM-DD) using pd.to_datetime() | 46065 | Closed | Affected East US and West Europe datasets
3 | Backend | 46075 | Lag variable generation produced NaN values for first N rows of each region group | Sprint 2 | Backend | Logical | Applied group-wise dropna() after lag feature creation; updated feature pipeline accordingly | 46076 | Closed | Occurred for lag=7 and lag=14 variables
4 | Backend | 46078 | Seasonality flags incorrectly assigned due to wrong fiscal calendar mapping for Azure billing cycles | Sprint 2 | Backend | Logical | Corrected fiscal month mapping and re-engineered seasonality indicators using correct Azure billing calendar | 46079 | Closed | Impacted 3 months of training data
5 | Backend | 46087 | ARIMA model throwing ValueError when time series contained non-stationarity without prior differencing | Sprint 3 | Backend | Logical | Applied ADF test before fitting; added auto-differencing step in preprocessing pipeline | 46088 | Closed | Resolved after stationarity check was added
6 | Backend | 46090 | XGBoost model trained on unscaled features resulting in high RMSE compared to baseline | Sprint 3 | Backend | Logical | Applied MinMaxScaler to numerical features before training; retrained model with scaled inputs | 46091 | Closed | RMSE reduced by ~18% post fix
7 | Backend | 46093 | Model evaluation script comparing MAE across different datasets incorrectly aligned forecast with actual values | Sprint 3 | Backend | Logical | Fixed index alignment by resetting indices after train-test split; evaluation results now correctly matched | 46094 | Closed | Affected Sprint 3 evaluation report
8 | Backend | 46102 | FastAPI /predict endpoint returning 500 error when input JSON had extra or unexpected fields | Sprint 4 | Backend | Logical | Added input validation using Pydantic schema with strict field definitions; unrecognized fields now rejected gracefully | 46103 | Closed | Fixed with proper request schema validation
9 | Frontend | 46106 | Dashboard line chart not rendering time-series forecast correctly due to date format mismatch in forecast_output.csv | Sprint 4 | Frontend | User Interface | Converted date column to string in ISO format before writing CSV; updated dashboard data loader to parse correctly | 46107 | Closed | Affected Power BI refresh pipeline
10 | Backend | 46108 | Batch prediction script failing silently when input CSV had missing rows for certain regions | Sprint 4 | Backend | Logical | Added row-level validation and logging; script now raises alert and skips invalid rows instead of silent failure | 46109 | Open | Monitoring added; full fix under review

## Sheet2
Logical
User Interface
Maintainability
Standards
Others